## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000159/2023-2024 | 1937/MURD | 18/07/2023 | 02/08/2023 | M/S BAPPA ENTERPRISE | 4.72 | 4.38 | 92.88 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000160/2023-2024 | 1938/MURD | 18/07/2023 | 02/08/2023 | M/S BAPPA ENTERPRISE | 3.66 | 3.5 | 95.57 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000161/2023-2024 | 1939/MURD | 18/07/2023 | 02/08/2023 | M/S BAPPA ENTERPRISE | 1.97 | 1.91 | 97 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Lalbagh Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000162/2023-2024 | 1940/MURD | 18/07/2023 | 02/08/2023 | M/S BAPPA ENTERPRISE | 3.49 | 2.96 | 84.67 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Kandi Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000163/2023-2024 | 1941/MURD | 18/07/2023 | 02/08/2023 | M/S BAPPA ENTERPRISE | 3.29 | 3.05 | 92.72 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Printing and supply of 20572 nos. FTK data sheet at sub-district water testing laboratories of Murshidabad on A4 size good quality paper (GSM75) as per format supply by the department for the purpose of water sample data collection by ASHA Workers. To be engaged in gram panchayat under different block for testing of water samples through FTK under Murshidabad Division, PHE Dte.(Soft copy of printing material will be supplied by the office). | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000899/2022-2023 | 343/HQ | 29/12/2022 | 08/01/2023 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 0.98 | 0.98 | 100 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En | SM/13045 | Support-WQMSP | Transfer of fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK). Ref Memo No - HFW-27099/408/2022-MSD. MB NO - 7068 |  |  | VCH/001021/2022-2023 | 407-MSD/22-23 | 23/11/2022 |  | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 25.5 | 0 | 0 | 0
Total | [13 empty] | 43.62 | 16.78 | 38.48