## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | New | Formal work order for the work of LOHADAHA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362288S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000707/2022-2023 | 146/MURD | 17/01/2023 | 17/01/2024 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 492.18 | 143.38 | 29.13 | 40
2 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1004/MURD/17 | 17/04/2023 |  | Resource Division | 36.62 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | New | Lohadaha PH-1 Application No- 3004528444 |  |  | BILL/01202/2023-2024 | 280/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.67 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | New | Quotation for Lohadaha PH-2 |  |  | BILL/01432/2023-2024 | 331/WBSEDCL-JJM | 07/02/2024 |  | WBSEDCL | 5.54 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS | SM/13727 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under LOHADAHA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000099/2023-2024 | 1890/MEDB | 16/06/2023 | 14/09/2023 | M/S SWAPAN BANERJEE | 24.36 | 10.29 | 42.25 | 15
Total | [13 empty] | 562.37 | 153.67 | 27.32