## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | Formal work order for the work of GARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000690/2022-2023 | 144/MURD | 17/01/2023 | 17/01/2024 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 583.49 | 69.36 | 11.89 | 31
2 | MURSHIDABAD | Khargram | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1067/MURD/2 | 18/04/2023 |  | Resource Division | 27.8 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | Material Requisition To Resource Division |  |  | RTOR000337/2023-2024 | 79/MURD/04 | 09/01/2024 |  | Resource Division | 18.58 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | NEW SERVICE CONNECTION AT PH2 GURULIA ID 304239443 |  |  | BILL/01412/2023-2024 | 309/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 4.29 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | NEW SERVICE CONNECTION AT PH1 GURULIA ID 304239442 |  |  | BILL/01413/2023-2024 | 310/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 4.23 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS | SM/13924 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GARULIA ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000152/2023-2024 | 2013/MEDB | 19/06/2023 | 17/09/2023 | JOGMAYA ENGINEERING | 24.48 | 9.96 | 40.67 | 50
Total | [13 empty] | 662.88 | 79.32 | 11.97