## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Allied work for KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000052/2024-2025 | 1977/MURD | 08/07/2024 | 06/09/2024 | DAS TRADING CO. | 70.58 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Formal work order for the work of KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000679/2022-2023 | 38/MURD | 04/01/2023 | 04/01/2024 | PRADIP KUMAR DAS | 720.99 | 278.1 | 38.57 | 35
3 | MURSHIDABAD | Khargram | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1067/MURD | 18/04/2023 |  | Resource Division | 15.98 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Electric Service Connection at KESHAR PH I, Application NO.3004403775, ID 304120001 |  |  | BILL/01058/2023-2024 | 192/WBSEDCL-JJM | 19/12/2023 |  | WBSEDCL | 5.11 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Electric Service Connection at KHESAR PWSS PH II, Application NO.3004403805, ID 304120021 |  |  | BILL/01076/2023-2024 | 193/WBSEDCL-JJM | 19/12/2023 |  | WBSEDCL | 4.51 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHESAR AND IT'S ADJOINING MOUJAS PWSS | SM/13937 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KHESAR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000149/2023-2024 | 2012/MEDB | 19/06/2023 | 17/09/2023 | M/S. SUPER CONSTRUCTION | 26.01 | 5.9 | 22.68 | 30
Total | [13 empty] | 843.19 | 284 | 33.68