## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | Formal work order for the work of EKPAHARIA (Part-A) & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000718/2022-2023 | 104/MURD | 13/01/2023 | 13/01/2024 | DOBAY CONSTRUCTION | 422.08 | 60.37 | 14.3 | 18
2 | MURSHIDABAD | Burwan | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | Formal work order for the work of EKPAHARIA( Part-B) & adjoining moujas PWSS to accommodate Construction Tube Well, Pump House Cum Chlorine Room & Blower room and Laying Distribution System under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000719/2022-2023 | 105/MURD | 13/01/2023 | 12/07/2023 | MOTI RAHAMAN | 203.57 | 111.79 | 54.91 | 45
3 | MURSHIDABAD | Burwan | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1067/MURD/5 | 18/04/2023 |  | Resource Division | 25.69 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | NEW SERVICE CONNECTION AT PWSS PH 2 EKPAHARIA ID 304247011 |  |  | BILL/01422/2023-2024 | 319/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 6.8 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | NEW SERVICE CONNECTION AT PWSS PH1 EKPAHARIA ID 304248191 |  |  | BILL/01424/2023-2024 | 320/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 5.56 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS | SM/14497 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under EKPAHARIA ground water based water supply scheme under Block_ Burwan, Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000709/2023-2024 | 4062/MEDB | 04/12/2023 | 03/03/2024 | PADMA ENGINEERING CO | 24.19 | 0 | 0 | 0
Total | [13 empty] | 687.9 | 172.16 | 25.03