## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | New | KOGRAM & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER_BURWAN BLOCK | ORD/000013/2023-2024 | 983/MURD | 10/04/2023 | 09/04/2024 | HIRANMAY GHOSH | 599.93 | 14.85 | 2.47 | 30
2 | MURSHIDABAD | Burwan | Murshidabad Division | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | New | Material Requisition To Resource Division |  |  | RTOR000242/2023-2024 | 1219/MURD/17 | 03/05/2023 |  | Resource Division | 14.53 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | New | Kogram PH-2 Application No-3004543754 |  |  | BILL/01178/2023-2024 | 238/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 4.36 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | New | Kogram PH-1 Application No- 3004543655 |  |  | BILL/01179/2023-2024 | 239/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 5.47 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS | SM/14507 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KOGRAM ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000689/2023-2024 | 4303/MEDB | 29/12/2023 | 28/03/2024 | DAS ENTERPRISE (CHOA) | 23.66 | 0 | 0 | 0
Total | [13 empty] | 647.94 | 14.85 | 2.29