## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gafulia & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000049/2023-2024 | 1218/MURD | 03/05/2023 | 02/06/2023 | MAMATA USHA ENTERPRISE | 21.38 | 9.47 | 44.28 | 100
2 | MURSHIDABAD | Burwan | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Laying Distribution System (PART-B), FHTC in GAFULIA Water at Supply Scheme in Burwan Block , under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000152/2023-2024 | 1900/MURD | 17/07/2023 | 14/11/2023 | MITRA CONSTRUCTION | 263.45 | 22.04 | 8.37 | 31
3 | MURSHIDABAD | Burwan | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Formal work order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall of GAFULIA PWSS, in Burwan Block under Murshidabad Division ,PHE.Dte. [ (i)Amount for LDS , R. Main : Rs. 52,45,981.00 & (ii) Amount for OHR, & Pump House : Rs. 1,56,36,015.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000792/2022-2023 | 592/MURD | 01/03/2023 | 29/02/2024 | H.L. CONSTRUCTION (TITAN BISWAS) | 208.8 | 51.74 | 24.78 | 30
4 | MURSHIDABAD | Burwan | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 1278/MURD/17 | 10/05/2023 |  | Resource Division | 27.87 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Material Requisition To Resource Division |  |  | RTOR000334/2023-2024 | 79/MURD/01 | 09/01/2024 |  | Resource Division | 12.43 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Electric Service Connection at GAFULIA RAJHAT SIULI PWSS PH II, Application NO.3004502793, ID 304199818 |  |  | BILL/01082/2023-2024 | 191/WBSEDCL-JJM | 19/12/2023 |  | WBSEDCL | 6.85 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | New service connection at SULI PH1 ID 304199844 |  |  | BILL/01125/2023-2024 | 225/WBSEDCL-JJM | 08/01/2024 |  | WBSEDCL | 5.06 | 0 | 0 | 0
8 | MURSHIDABAD | Burwan | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS | SM/14626 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GAFULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000062/2023-2024 | 1928/MEDB | 16/06/2023 | 14/09/2023 | WEST BENGAL ENGINEERING CO. | 23.39 | 0 | 0 | 0
Total | [13 empty] | 569.23 | 83.24 | 14.62