## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | SUBMISSION OF ONE NO REPAIRING ESTIMATE OF ROAD WHICH IS DAMAGED DURING PHE PIPE LINE LAYING IE. |  |  | BILL/00655/2024-2025 | 282-MSD/2024-25 | 13/08/2024 | 13/08/2024 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 20.84 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | Augmentation of Ground Water Based Narsinghpur Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000276/2023-2024 | 2617/MURD | 22/08/2023 | 27/04/2025 | RAJKUMAR MONDAL | 202.06 | 0 | 0 | 55
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER |  | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 16.51 | 2.61 | 15.83 | 1
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundary wall for Augmentation of NARASINGHAPUR Zone-II PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte.PART_B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000594/2023-2024 | 3333/MURD | 23/10/2023 | 30/04/2025 | GOUTAM MANDAL | 142.16 | 0 | 0 | 40
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000241/2023-2024 | 1219/MURD/23 | 03/05/2023 | 03/05/2023 | Resource Division | 16.53 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | NEW SERVICE CONNECTION AT NARASINGHAPUR PWSS Z2 JL NO14 PLOT NO 970,1030,974 ID 304238697 |  |  | BILL/01271/2023-2024 | 294/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | AT NARASINGHAPUR PWSS Z2 PH 1 ID 304238696 |  |  | BILL/01481/2023-2024 | 448/WBSEDCL-JJM | 15/03/2024 | 15/03/2024 | WBSEDCL | 9.32 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15066 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Narsinghpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001508/2023-2024 | 584/MEDB | 31/01/2024 | 01/07/2025 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 20.81 | 0 | 0 | 70
Total | [13 empty] | 432.4 | 2.61 | 0.6