## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | Augmentation | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 28/08/2024 | M/S. MOHAN LAL JAIN | 2092.12 | 307.65 | 14.71 | 56
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER |  | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 01/12/2022 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000255/2023-2024 | 1219/MURD/40 | 03/05/2023 |  | Resource Division | 69.3 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000388/2023-2024 | 526/MURD/05 | 19/02/2024 |  | Resource Division | 14.88 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. | SM/15069 | Augmentation | SHIFTING OF HT LINE AT RAJAPUR ID 860296030 |  |  | BILL/00178/2024-2025 | 17/WBSEDCL-JJM | 16/04/2024 |  | WBSEDCL | 4.36 | 0 | 0 | 0
Total | [13 empty] | 2197.18 | 307.65 | 14