## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 28/07/2024 | IMAGIN | 95.53 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Providing FHTC Connection to 1159 nos household for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE.Dte. (part_C) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000100/2023-2024 | 1699/MURD | 28/06/2023 | 27/08/2023 | S. ROY & CO. | 67.64 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Construction of 300 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 180 Cum capacity, Construction of Boundary Wall for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte. (part_A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000195/2023-2024 | 2038/MURD | 26/07/2023 | 25/07/2024 | SATELLITE CONSTRUCTION | 177.33 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Laying of Distribution System, Construction Pump House with sanitary and Water Supply Arrangement, Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing Pump House and Allied Works for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte.(part _B) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000196/2023-2024 | 2037/MURD | 26/07/2023 | 22/01/2024 | AMIT KUMAR GUPTA | 176.87 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 04/04/2022 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 0 | 0.86
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 1811/MURD/15 | 20/06/2024 |  | Resource Division | 8.19 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000212/2023-2024 | 1219/MURD/03 | 03/05/2023 |  | Resource Division | 22.93 | 0 | 0 | 0
9 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . | SM/15268 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 22018.43 | 0 | 0