## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Allied work for Construction of Boundary wall, Road repair & 1 no. Box Culvert at Kirtipur PWSS at Khargram Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000062/2024-2025 | 1990/MURD | 08/07/2024 | 06/10/2024 | ARIZ ENTERPRISE | 36.54 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Formal work order for KIRTTIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000848/2022-2023 | 781/MURD | 20/03/2023 | 25/12/2023 | ARIZ ENTERPRISE | 343.69 | 49.22 | 14.32 | 11
3 | MURSHIDABAD | Khargram | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1129/MURD/6 | 25/04/2023 |  | Resource Division | 10.76 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Material Requisition To Resource Division |  |  | RTOR000341/2023-2024 | 79/MURD/08 | 09/01/2024 |  | Resource Division | 9.85 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Electric Service Connection at KRITTIPUR PWSS PH I, Application NO.3004450962, ID 304158425 |  |  | BILL/01079/2023-2024 | 189/WBSEDCL-JJM | 19/12/2023 |  | WBSEDCL | 4.87 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | NEW SERVICE CONNECTION AT PWSS PH2 KIRTIPUR ID304239452 |  |  | BILL/01416/2023-2024 | 304/WBSEDCL-JJM | 05/02/2024 |  | WBSEDCL | 3.41 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS | SM/15691 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kirttipur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000271/2023-2024 | 3709/MEDB | 03/11/2023 | 01/02/2024 | WEST BENGAL ENGINEERING CO. | 22.18 | 0 | 0 | 0
Total | [13 empty] | 431.3 | 49.22 | 11.41