## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | Providing FHTC Connection to 1050 nos household , Construction of 450 Cum OHR, Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement for Augmentation work of REJINAGAR ZONE-IV Beldanga -II Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000258/2023-2024 | 2469/MURD | 09/08/2023 | 08/08/2024 | M/S. S.C. CIVIL ENTERPRISES | 482.41 | 0 | 0 | 36
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 13/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 0 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 1811/MURD/22 | 20/06/2024 |  | Resource Division | 6.47 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000221/2023-2024 | 1219/MURD/24 | 03/05/2023 |  | Resource Division | 51.16 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | NEW CONNECTION REJINAGAR Z-IV PH-I |  |  | BILL/01580/2023-2024 | 421/WBSEDCL-JJM | 06/03/2024 |  | WBSEDCL | 3.61 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. | SM/15748 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IV under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000239/2023-2024 | 3675/MEDB | 03/11/2023 | 01/02/2024 | SREE RADHA ELECTRICAL | 25.04 | 9.41 | 37.59 | 7
Total | [13 empty] | 588.63 | 9.41 | 1.6