## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 09/06/2022 | RADIANT | 73.97 | 0 | 0 | 100
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Augmentation Work of Harua Part A Piped Water Supply Scheme to accommodate with Laying of Rising Main , Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000144/2023-2024 | 1868/MURD | 14/07/2023 | 10/01/2024 | PAL CONSTRUCTION | 31 | 16.62 | 53.62 | 28
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 72.00Cum/hr.) at Harua Water Supply Scheme under Jal Jivan Mission of Suti-I Block under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000822/2023-2024 | 743/MURD | 12/03/2024 | 11/04/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 63.59 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 1219/MURD/22 | 03/05/2023 |  | Resource Division | 20.71 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Harua PH-3 Application No- 3004555905 |  |  | BILL/01198/2023-2024 | 275/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 8.65 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. | SM/15752 | Augmentation | Harua PH-1 Application No- 3004555901 |  |  | BILL/01199/2023-2024 | 276/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 2.16 | 0 | 0 | 0
Total | [13 empty] | 200.08 | 16.62 | 8.31