## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Basantapur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000037/2023-2024 | 1104/MURD | 24/04/2023 | 24/05/2023 | NADIA TUBEWELLS | 21.35 | 4.4 | 20.6 | 50
2 | MURSHIDABAD | Khargram | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASANTPUR AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000290/2023-2024 | 2656/MURD | 24/08/2023 | 14/09/2023 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 0
3 | MURSHIDABAD | Khargram | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | Laying Distribution System , Rising Main Connection FHTC, Construction of Pump House & Boundary Wall for Basantapur water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000892/2022-2023 | 929/MURD | 31/03/2023 | 29/07/2023 | PARTHA PRATIM DAS | 61.73 | 14.18 | 22.98 | 30
4 | MURSHIDABAD | Khargram | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 1075/MURD/7 | 19/04/2023 |  | Resource Division | 18.61 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | NEW SERVICE CONNECTION AT BASANTIPUR PH I, ID304233690 |  |  | BILL/01212/2023-2024 | 274/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 4.96 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | BASANTAPUR AND ADJOINING MOUJAS PWSS | SM/15940 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BASANTAPUR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000050/2023-2024 | 1924/MEDB | 16/06/2023 | 14/09/2023 | MAHADEB ENTERPRISE | 20.81 | 0 | 0 | 0
Total | [13 empty] | 145.91 | 18.58 | 12.74