## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- B village, Block:- Khargram, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000230/2023-2024 | 2341/MURD | 03/08/2023 | 02/10/2023 | J.S. CONSTRUCTION | 30.54 | 0 | 0 | 0
2 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- C village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000231/2023-2024 | 2342/MURD | 03/08/2023 | 02/10/2023 | M/S SAJAHAN CHOWDHURY | 30.48 | 0 | 0 | 10
3 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- E village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000233/2023-2024 | 2343/MURD | 03/08/2023 | 02/10/2023 | SUGATA CHOWDHURY | 30.55 | 7.64 | 24.99 | 10
4 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- A village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000254/2023-2024 | 2494/MURD | 11/08/2023 | 10/10/2023 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 30.55 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- D village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000478/2023-2024 | 3035/MURD | 27/09/2023 | 26/11/2023 | S.N. ENTERPRISE | 29.6 | 0 | 0 | 10
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kharsa Part-A village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000201/2023-2024 | 3061/MEDB | 02/08/2023 | 31/10/2023 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0 | 0
7 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kharsa Part-B village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000202/2023-2024 | 3062/MEDB | 02/08/2023 | 31/10/2023 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
8 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kharsa Part-C village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000203/2023-2024 | 3063/MEDB | 02/08/2023 | 31/10/2023 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
9 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kharsa Part-D village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000204/2023-2024 | 3064/MEDB | 02/08/2023 | 31/10/2023 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
10 | MURSHIDABAD | Khargram | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. | SM/16051 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kharsa Part-E village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000205/2023-2024 | 3065/MEDB | 02/08/2023 | 31/10/2023 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
Total | [13 empty] | 182.93 | 7.64 | 4.17