## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | New | Providing FHTC Connection to 510 nos household , Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement & Construction Pump House cum Blower room cum Chlorine room with out sanitary and Water Supply Arrangement RANAGRAM PWSS KANDI Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER_KANDI BLOCK | ORD/000244/2023-2024 | 2432/MURD | 08/08/2023 | 04/02/2024 | R.R. CONSTRUCTION | 70.39 | 0 | 0 | 30
2 | MURSHIDABAD | Kandi | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1129/MURD | 25/04/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Central Drilling | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 29/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 3.8 | 3.42 | 0
4 | MURSHIDABAD | Kandi | Berhampore Mechanical | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | New | NEW SERVICE CONNECTION AT RANAGRAM PH I, ID304236076 |  |  | BILL/01211/2023-2024 | 271/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 8.48 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Berhampore Mechanical | RANAGRAM AND ADJOINIG MOUJAS PWSS | SM/16052 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ranagram ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000257/2023-2024 | 3693/MEDB | 03/11/2023 | 01/02/2024 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 0 | 0
Total | [13 empty] | 212.25 | 3.8 | 1.79