## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | Allied works for laying pipeline and construction of approach road for Fatepur Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000063/2024-2025 | 1978/MURD | 08/07/2024 | 06/09/2024 | ABIDA CONSTRUCTION | 19.77 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | FATEPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000141/2023-2024 | 1867/MURD | 14/07/2023 | 11/11/2023 | ABIDA CONSTRUCTION | 124.31 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | Laying and distribution of UPVC pipeline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000185/2022-2023 | 192/BSD | 28/04/2022 | 28/05/2022 | SURAJIT MONDAL | 4.77 | 2.32 | 48.72 | 100
4 | MURSHIDABAD | Burwan | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | Repair and renovation work of Switch room and Boundary wall at Head Work and 2nd TW site of Fatepur Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001680/2021-2022 | 17/BSD | 10/01/2022 | 09/02/2022 | MADAN MOHAN SASMAL | 4.85 | 4.41 | 90.86 | 100
5 | MURSHIDABAD | Burwan | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 1936/MURD/6 | 19/07/2023 |  | Resource Division | 1.09 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Central Drilling | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000209/2023-2024 | 2203/CDD | 01/03/2024 | 29/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 0
7 | MURSHIDABAD | Burwan | Berhampore Mechanical | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme | SM/16113 | New | POWER CONNECTION AT PWSS FATEPUR PH 1 ID 304248214 |  |  | BILL/00183/2024-2025 | 43/WBSEDCL-JJM | 22/04/2024 |  | WBSEDCL | 4.71 | 0 | 0 | 0
Total | [13 empty] | 270.56 | 6.73 | 2.49