## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Jalangi | Murshidabad Division | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. | SM/16209 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 15/09/2023 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 0 | 100
2 | MURSHIDABAD | Jalangi | Murshidabad Division | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. | SM/16209 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 01/12/2022 | MERCHANDISE-INDIA | 14.45 | 0 | 0 | 90
3 | MURSHIDABAD | Jalangi | Berhampore Mechanical | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. | SM/16209 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Ramprasad village, Block:- Jalangi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000687/2023-2024 | 3628/MEDB | 03/11/2023 | 01/02/2024 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
Total | [13 empty] | 29.98 | 0 | 0