## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Samserganj | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | CHANDNI DAHA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main ,Construction of OHR of 300 cum capacity, Construction Pump House cum Chlorine Room (5.90m x 4.1m) & Pump House (4.10m x 3.5m) with sanitary and Water Supply Arrangement) & Construction of 190 m Boundary wall under Jal Jeevan Mission of Samserganj Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000447/2023-2024 | 2968/MURD | 20/09/2023 | 19/09/2024 | M/S GOLAM KIBRIA | 431.64 | 0 | 0 | 0
2 | MURSHIDABAD | Samserganj | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
3 | MURSHIDABAD | Samserganj | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 1219/MURD/14 | 03/05/2023 |  | Resource Division | 19.83 | 0 | 0 | 0
4 | MURSHIDABAD | Samserganj | Central Drilling | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | MURSHIDABAD | Samserganj | Berhampore Mechanical | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | NEW CONNECTION AT CHANDNIDAHA PH-II |  |  | BILL/00420/2024-2025 | 141/WBSEDCL-JJM | 08/07/2024 |  | WBSEDCL | 10.1 | 0 | 0 | 0
6 | MURSHIDABAD | Samserganj | Berhampore Mechanical | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . | SM/16217 | New | NEW CONNECTION AT CHANDNIDAHA PH-I |  |  | BILL/00421/2024-2025 | 142/WBSEDCL-JJM | 08/07/2024 |  | WBSEDCL | 11.52 | 0 | 0 | 0
Total | [13 empty] | 22066.1 | 0 | 0