## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Allied work for road restoration work liable to be damaged due to pipeline laying at Parbotipur PWSS under Kandi sub-Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000037/2024-2025 | 1912/MURD | 02/07/2024 | 31/08/2024 | DIPAK KUMAR GHOSH | 42.14 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW- III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PARBATIPUR AND ADJOINING MOUJAS Water Supply Scheme at 3rd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER |  | ORD/000402/2023-2024 | 2821/MURD | 07/09/2023 | 21/09/2023 | INDRAJIT MAZUMDAR | 9.22 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Formal work order for PARBATIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KANDI of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000818/2022-2023 | 675/MURD | 09/03/2023 | 14/12/2023 | DIPAK KUMAR GHOSH | 467.48 | 51.04 | 10.92 | 25
4 | MURSHIDABAD | Kandi | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1129/MURD/3 | 25/04/2023 |  | Resource Division | 15.8 | 0 | 0 | 0
5 | MURSHIDABAD | Kandi | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Material Requisition To Resource Division |  |  | RTOR000339/2023-2024 | 79/MURD/06 | 09/01/2024 |  | Resource Division | 12.55 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Service connection charge for Parbbatipur SM/ 16393 |  |  | BILL/01093/2023-2024 | 200/WBSEDCL-JJM | 19/12/2023 |  | WBSEDCL | 19.26 | 0 | 0 | 0
7 | MURSHIDABAD | Kandi | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | NEW SERVICE CONNECTION AT PARBATIPUR PH II, ID304236105 |  |  | BILL/01210/2023-2024 | 293/WBSEDCL-JJM | 01/02/2024 |  | WBSEDCL | 3.28 | 0 | 0 | 0
8 | MURSHIDABAD | Kandi | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16393 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Parbbatipur ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000275/2023-2024 | 3715/MEDB | 03/11/2023 | 01/02/2024 | M/S SAJAHAN CHOWDHURY | 23.87 | 9.88 | 41.38 | 15
Total | [13 empty] | 593.61 | 60.92 | 10.26