## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Allied work of connection of Rising and Distribution main with supply of materials and construction of sluice valve chamber at Char Mahula water supply scheme under Berhampore sub division, P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000054/2024-2025 | 1985/MURD | 08/07/2024 | 06/09/2024 | SUPIA CONSTRUCTION | 4.47 | 0 | 0 | 85
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Augmentation of CHARMAHULA PWSS under Jal Jeevan Mission of BERHAMPORE Block, BERHAMPORE Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000528/2023-2024 | 3119/MURD | 05/10/2023 | 11/07/2024 | M/S. BHABESH HALDER | 249.71 | 0 | 0 | 25
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 04/04/2022 | ENVIROTECH SOLUTIONS | 32.69 | 2.39 | 7.32 | 0.86
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 1811/MURD/16 | 20/06/2024 |  | Resource Division | 20.22 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 1180/MURD/02 | 29/04/2023 |  | Resource Division | 18.43 | 0 | 0 | 0
6 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. | SM/16418 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21665.29 | 2.39 | 0.01