## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- A village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000215/2023-2024 | 2330/MURD | 02/08/2023 | 01/10/2023 | MADAN MOHAN SASMAL | 30.55 | 10.15 | 33.21 | 20
2 | MURSHIDABAD | Bharatpur - II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000219/2023-2024 | 2328/MURD | 02/08/2023 | 01/10/2023 | SARTHAK SK. | 30.55 | 5.26 | 17.21 | 25
3 | MURSHIDABAD | Bharatpur - II | Murshidabad Division | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Ground Water based piped water supply scheme for Jaulia Part- C village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000220/2023-2024 | 2339/MURD | 03/08/2023 | 02/10/2023 | MAHATO ENTERPRISE | 30.55 | 5.07 | 16.61 | 10
4 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT JAULIA PH-II |  |  | BILL/00232/2024-2025 | 64/WBSEDCL-JJM | 09/05/2024 |  | WBSEDCL | 3.29 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT MATWA PH-II |  |  | BILL/00235/2024-2025 | null | 02/05/2024 |  | WBSEDCL | 4.25 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT JAULIA PH-I |  |  | BILL/00240/2024-2025 | null | 09/05/2024 |  | WBSEDCL | 4.25 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | NEW CONNECTION AT JAULIA PH-I |  |  | BILL/00246/2024-2025 | 77/WBSEDCL-JJM | 20/05/2024 |  | WBSEDCL | 4.25 | 0 | 0 | null
8 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jaulia Part-A village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000198/2023-2024 | 3057/MEDB | 02/08/2023 | 31/10/2023 | MONI ELECTRICAL WORKS | 6.27 | 0 | 0 | 0
9 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jaulia Part-B village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000199/2023-2024 | 3058/MEDB | 02/08/2023 | 31/10/2023 | QUAZI NOZRUL ISLAM | 6.27 | 0 | 0 | 0
10 | MURSHIDABAD | Bharatpur - II | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. | SM/16445 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jaulia Part-C village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000200/2023-2024 | 3060/MEDB | 02/08/2023 | 31/10/2023 | QUAZI NOZRUL ISLAM | 6.27 | 0 | 0 | 0
Total | [13 empty] | 126.49 | 20.48 | 16.19