## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | SUNUTI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, BHARARPUR-I of Murshidabad District under Kandi sub division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000867/2022-2023 | 846/MURD | 24/03/2023 | 23/03/2024 | M/S. BIMALENDU BOSE | 471.09 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur - I | Murshidabad Division | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1075/MURD/1 | 19/04/2023 |  | Resource Division | 19.17 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | NEW CONNECTION AT SUNUTI PH-II |  |  | BILL/00404/2024-2025 | null | 28/05/2024 |  | WBSEDCL | 4.22 | 0 | 0 | 0
4 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | NEW CONNECTION AT SUNUTI PH-II |  |  | BILL/00406/2024-2025 | 103/WBSEDCL-JJM | 06/06/2024 |  | WBSEDCL | 4.22 | 0 | 0 | null
5 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | Sunuti PH-1 Application No- 3004528432 |  |  | BILL/01200/2023-2024 | 265/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.59 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur - I | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME | SM/16549 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUNUTI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000119/2023-2024 | 1908/MEDB | 16/06/2023 | 14/09/2023 | M/S S. R. ENTERPRISE | 23.39 | 0 | 0 | 0
Total | [13 empty] | 525.68 | 0 | 0