## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti - II | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 0 | 0 | 100
2 | MURSHIDABAD | Suti - II | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKAIPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000616/2023-2024 | 3388/MURD | 01/11/2023 | 22/11/2023 | TAPAN DAS | 18.56 | 7.38 | 39.74 | 80
3 | MURSHIDABAD | Suti - II | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Formal Work Order for LOKAIPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000829/2022-2023 | 694/MURD | 10/03/2023 | 09/03/2024 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 239.71 | 24.04 | 10.03 | 30
4 | MURSHIDABAD | Suti - II | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 1230/MURD/26 | 04/05/2023 |  | Resource Division | 18.15 | 0 | 0 | 0
5 | MURSHIDABAD | Suti - II | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Material Requisition To Resource Division |  |  | RTOR000374/2023-2024 | 495/MURD/07 | 15/02/2024 |  | Resource Division | 4.1 | 0 | 0 | 0
6 | MURSHIDABAD | Suti - II | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | NEW CONNECTION LOKAIPUR PH-II |  |  | BILL/00166/2024-2025 | 9/WBSEDCL-JJM | 09/04/2024 |  | WBSEDCL | 4.73 | 0 | 0 | null
7 | MURSHIDABAD | Suti - II | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | LOKAIPUR PH-1 NEW CONNECTION |  |  | BILL/01487/2023-2024 | 389/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 3.85 | 0 | 0 | 0
8 | MURSHIDABAD | Suti - II | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | NEW CONNECTION LOKAIPUR PH-II |  |  | BILL/01662/2023-2024 | null | 27/03/2024 |  | WBSEDCL | 4.73 | 0 | 0 | 0
9 | MURSHIDABAD | Suti - II | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. | SM/16552 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube well in connection to Accommodate FHTC at Pump House No.-I II & III under LOKAIPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000695/2023-2024 | 3809/MEDB | 03/11/2023 | 01/02/2024 | DEBJYOTI BASU | 31.24 | 0 | 0 | 10
Total | [13 empty] | 578.31 | 31.42 | 5.43