## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Khargram | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | BISWANATHPUR PWSS under Jal Jeevan Mission of KHARGRAM Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000169/2023-2024 | 1975/MURD | 20/07/2023 | 17/11/2023 | AMAL KUMAR DAS | 126.72 | 10.11 | 7.98 | 70
2 | MURSHIDABAD | Khargram | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BISWANATHPUR Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000387/2023-2024 | 2777/MURD | 01/09/2023 | 22/09/2023 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 90
3 | MURSHIDABAD | Khargram | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 1129/MURD/4 | 25/04/2023 |  | Resource Division | 1.78 | 0 | 0 | 0
4 | MURSHIDABAD | Khargram | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | NEW SERVICE CONNECTION AT BISWANATHPUR PH II, ID304233616 |  |  | BILL/01214/2023-2024 | 262/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 7.78 | 0 | 0 | 0
5 | MURSHIDABAD | Khargram | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | NEW SERVICE CONNECTION AT BISWANATHPUR PH I, ID304233599 |  |  | BILL/01216/2023-2024 | 264/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.24 | 0 | 0 | 0
6 | MURSHIDABAD | Khargram | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. | SM/16553 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Biswanathpur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000266/2023-2024 | 3703/MEDB | 03/11/2023 | 01/02/2024 | M/S S. S. ENTERPRISE (DOMKAL) | 20.82 | 0 | 0 | 0
Total | [13 empty] | 178.8 | 10.11 | 5.65