## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000108/2023-2024 | 1750/MURD | 06/07/2023 | 27/07/2023 | MAMATA USHA ENTERPRISE | 27.67 | 8.56 | 30.92 | 67
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER |  | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 24/09/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Providing FHTC Connection to 390 nos household , Laying of Distribution System, Rising Main , Construction of Pump House & Boundary Wall, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr, Special repair and renovation of existing Pump House and Alied Works, Repairing & Vertical Extention of Boundary Wall for Augmentation work of MAHAMMADPUR PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000876/2022-2023 | 898/MURD | 29/03/2023 | 25/09/2023 | AJOY GHOSH | 171.58 | 65.3 | 38.06 | 40
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C |  | JUNIOR ENGINEER 1,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 0 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  | JUNIOR ENGINEER 1 | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 23/04/2022 | M/S. UNIQUE BUILDERS | 29.37 | 0 | 0 | 1
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. | SM/16623 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under MAHAMMADPUR ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000124/2023-2024 | 1911/MEDB | 16/06/2023 | 14/09/2023 | HANNAN BUILDERS PVT LTD | 44.47 | 0 | 0 | 70
Total | [13 empty] | 355.76 | 73.85 | 20.76