## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Augmentation of BILASPUR PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000079/2023-2024 | 1385/MURD | 22/05/2023 | 26/02/2024 | ULTRA CONSTRUCTION. | 227.02 | 67.3 | 29.64 | 45
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. | SM/16866 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 1180/MURD/04 | 29/04/2023 |  | Resource Division | 19.59 | 0 | 0 | 0
Total | [13 empty] | 246.61 | 67.3 | 27.29