## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Continuation Work Order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months.(Period From 31.05.2024 to 27.09.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000079/2024-2025 | 92/KSD | 27/05/2024 | 24/09/2024 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Augmentation of Ground Water Based Salar PWSS Zone-IA, IB, IIA, IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER |  | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 06/05/2024 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER |  | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 02/09/2024 | SUJIT KUMAR SAHA | 575.6 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur -II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000718/2023-2024 | 3835/MURD | 14/12/2023 | 04/01/2024 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 0 | 0 | 80
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. | SM/16899 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 04/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 0 | 76
Total | [13 empty] | 1783.32 | 0 | 0