## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Suti - II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | UMARPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000206/2023-2024 | 2290/MURD | 01/08/2023 | 31/07/2024 | CHAKRABORTY CONSTRUCTION | 916.93 | 26.31 | 2.87 | 10
2 | MURSHIDABAD | Suti - II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UMARPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000277/2023-2024 | 2606/MURD | 22/08/2023 | 12/09/2023 | INDRAJIT MAZUMDAR | 27.66 | 0 | 0 | 70
3 | MURSHIDABAD | Suti - II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 26/12/2022 | RADIANT | 253.25 | 12.12 | 4.79 | 100
4 | MURSHIDABAD | Suti - II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 1230/MURD/24 | 04/05/2023 |  | Resource Division | 132.07 | 0 | 0 | 0
5 | MURSHIDABAD | Suti - II | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Material Requisition To Resource Division |  |  | RTOR000379/2023-2024 | 495/MURD/02 | 15/02/2024 |  | Resource Division | 31.56 | 0 | 0 | 0
6 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-III |  |  | BILL/00168/2024-2025 | 6/WBSEDCL-JJM | 09/04/2024 |  | WBSEDCL | 3.49 | 0 | 0 | null
7 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-II |  |  | BILL/00169/2024-2025 | 7/WBSEDCL-JJM | 09/04/2024 |  | WBSEDCL | 3.73 | 0 | 0 | null
8 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-I |  |  | BILL/00170/2024-2025 | 8/WBSEDCL-JJM | 09/04/2024 |  | WBSEDCL | 3.5 | 0 | 0 | null
9 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-III |  |  | BILL/01658/2023-2024 | null | 27/03/2024 |  | WBSEDCL | 3.49 | 0 | 0 | 0
10 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-I |  |  | BILL/01659/2023-2024 | null | 27/03/2024 |  | WBSEDCL | 3.5 | 0 | 0 | 0
11 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | NEW CONNECTION UMRAPUR PH-II |  |  | BILL/01660/2023-2024 | null | 27/03/2024 |  | WBSEDCL | 3.73 | 0 | 0 | 0
12 | MURSHIDABAD | Suti - II | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . | SM/18472 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UMARPUR ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000456/2023-2024 | 3852/MEDB | 06/11/2023 | 04/02/2024 | SURAKSHA | 34.47 | 13.73 | 39.85 | 10
Total | [13 empty] | 1417.39 | 52.17 | 3.68