## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | BAIDYNATHPUR & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000222/2023-2024 | 2366/MURD | 04/08/2023 | 03/08/2024 | M/S.TAPAS KUMAR CHAKRABORTY | 867.57 | 86.53 | 9.97 | 10
2 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR ADJOINING MOUJA Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER |  | ORD/000399/2023-2024 | 2806/MURD | 05/09/2023 | 26/09/2023 | INDRAJIT MAZUMDAR | 27.64 | 0 | 0 | 0
3 | MURSHIDABAD | Burwan | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Material Requisition To Resource Division |  |  | RTOR000232/2023-2024 | 1219/MURD/16 | 03/05/2023 |  | Resource Division | 9.79 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Baidyanathpur PH1 Application no-3004548117 |  |  | BILL/01174/2023-2024 | 231/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 4.05 | 0 | 0 | 0
5 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Baidyanathpur PH-2 Application No- 3004548228 |  |  | BILL/01175/2023-2024 | 232/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 4.26 | 0 | 0 | 0
6 | MURSHIDABAD | Burwan | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS | SM/18580 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Baidynathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000261/2023-2024 | 3697/MEDB | 03/11/2023 | 01/02/2024 | P. K. ENGINEERING | 23.71 | 0 | 0 | 0
Total | [13 empty] | 937.02 | 86.53 | 9.23