## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Makimnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. |  |  | ORD/000065/2024-2025 | 1198/BD-I | 26/07/2024 | 24/09/2024 | BURIMAA CONSTRUCTION | 12.74 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mokimnagar (Village code 314172) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000203/2020-2021 | 969/BD-I | 17/12/2020 | 17/03/2021 | MS RUBIET HOSSAIN | 40.85 | 23.23 | 56.85 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Simulia (Village code 314155) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000204/2020-2021 | 970/BD-I | 17/12/2020 | 15/02/2021 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 6.79 | 5.24 | 77.23 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme | SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mridapur(Village code 314157) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000205/2020-2021 | 971/BD-I | 17/12/2020 | 17/03/2021 | MS RUBIET HOSSAIN | 33.94 | 28.8 | 84.86 | 1
Total | [13 empty] | 94.31 | 57.27 | 60.72