## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION at Sadatpur(VillageCode-315671) ,Chhatiai (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000116/2024-2025 | 1451/BD-I | 04/09/2024 | 04/10/2024 | K.S.ENTERPRISE (PROP. SAMIM SK.) | 3.55 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhatiani (Village code 315673) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2020-2021 | 1045/BD-I | 28/12/2020 | 28/03/2021 | MS RUBIET HOSSAIN | 43.95 | 39.68 | 90.3 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadatpur (Village code 315671) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000231/2020-2021 | 1046/BD-I | 28/12/2020 | 26/02/2021 | MAHATO ENTERPRISE | 4.04 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) | SM/07236 | Retrofitting | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II |  | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 13/03/2022 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0 | 0
Total | [13 empty] | 67.7 | 39.68 | 58.61