## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | SM/07688 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jagarpara (Village code 314183),Chamunda(Village code 314171),Janardanpur( Village code 314184), under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE | ORD/000127/2020-2021 | 203/BD-I | 04/02/2021 | 06/03/2021 | TARUN KUMAR BHATTACHARYA | 79.1 | 5.61 | 7.09 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr | SM/07688 | Retrofitting | Balance work of Planning Design, Investigation Construction Erection, Installation, Completion testing and commissioning in all respect of entire units of Arsenic cum Iron Removal Plant AIRP of different capacities( excluding Administrative Building) capable of removing Arsenic & Iron present in ground water in different concentration to acceptable limit by CPHEEO manual on basis of approved drawing of Modified Sujapur Sadipur Model including 3 months Trial Run & 9 (Months) Operation & Maintenance (Excluding Administrative Building) of different Blocks under Berhampore Div.-I in the District of Murshidabad , P. H. Engineering Dte. Name of Scheme: Nasipur W/S Scheme, Block: Lalgola, Capacity: 120cum/hr. Arsenic: 0.075 ppm, Iron-3.10 ppm. | Assistant Engineer-I | JE | ORD/000636/2019-2020 | 977/BD-I | 25/07/2019 | 23/07/2025 | ACQUA CONSTRUCTION CONSORTIUM | 143.89 | 6.97 | 4.84 | 1
Total | [13 empty] | 222.99 | 12.58 | 5.64