## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I |  |  | BILL/00065/2024-2025 | BP-2024-25-62 | 19/06/2024 | 19/06/2024 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 600 mm dia M.S Casing Pipe through 250 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station NLSF-LCAE at KM, 166-33/34-166/35/36 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I |  |  | BILL/00066/2024-2025 | BP-2024-25-63 | 19/06/2024 | 19/06/2024 | EASTERN RAILWAY HOWRAH DIVISION | 5.94 | 0 | 0 | 0
3 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I (for Raw Water) |  |  | BILL/00089/2024-2025 | BP-2024-25-65 | 20/06/2024 | 20/06/2024 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0 | 0
4 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION NLSF-LCAE AT KM 170/27-29 & 170/28-30 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. |  |  | BILL/00153/2024-2025 | BP-2024-25-114 | 30/07/2024 | 30/07/2024 | EASTERN RAILWAY HOWRAH DIVISION | 7.19 | 0 | 0 | 0
5 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. |  |  | BILL/00154/2024-2025 | BP-2024-25-115 | 30/07/2024 | 30/07/2024 | EASTERN RAILWAY HOWRAH DIVISION | 6.32 | 0 | 0 | 0
6 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 160/13-15 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. |  |  | BILL/00155/2024-2025 | BP-2024-25-116 | 30/07/2024 | 30/07/2024 | EASTERN RAILWAY HOWRAH DIVISION | 6.43 | 0 | 0 | 0
7 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. (R.A-2) |  |  | BILL/00175/2024-2025 | BP-2024-25-135 | 21/08/2024 | 21/08/2024 | EASTERN RAILWAY HOWRAH DIVISION | 0 | 0 | 0 | 0
8 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | HYDRAGRAPHIC SURVEY CHARGE FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART BERHAMPORE AND MURSHIDABAD JIAGANJ BLOCKS OF DISTRICT OF MURSHIDABAD |  |  | BILL/00208/2023-2024 | BP-2023-24-127 | 15/09/2023 | 15/09/2023 | SYAMA PRASAD MOOKERJEE PORT KOLKATA | 55.55 | 0 | 0 | 0
9 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Consultancy charges along with the work order in respect of the project title "EIA and EMP for proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad (IPBN) |  |  | BILL/00313/2023-2024 | BP-2023-24-205 | 13/12/2023 | 13/12/2023 | IIT CONSULTATIVE PRATICE | 5.52 | 0 | 0 | 0
10 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | safety checking of 2 (Two) nos over Head Reservoir under 1). Nabagram Ground water supply scheme, 2). Panchgram Ground water supply scheme, in Block Nabagram of Murshidabad District under P.H.Engineering Department Govt. of West Bengal. |  |  | BILL/00442/2024-2025 | BP-2024-25-266 | 17/01/2025 | 17/01/2025 | SRCC NIT DURGAPUR | 0.71 | 0 | 0 | 0
11 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Second Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad |  |  | BILL/00800/2023-2024 | BP-2023-24-290 | 01/03/2024 | 01/03/2024 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0 | 0
12 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Third Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad |  |  | BILL/00801/2023-2024 | BP-2023-24-291 | 01/03/2024 | 01/03/2024 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0 | 0
13 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 03.07.2024 to 30.06.2025]. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000040/2024-2025 | 1047/BD-I | 02/07/2024 | 02/07/2025 | AMAN CONSTRUCTION | 1.81 | 0 | 0 | 45
14 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | SUPPLY, CARRIAGE , LAYING AND COMMISSIONING OF DISTRIBUTION PIPE NETWORK INCLUDING PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) AND PIPED WATER SUPPLY ARRANGEMENT FOR DIFFERENT SCHOOL ,SSK, MSK ETC.OF DIFFERENT DISTRIBUTION ZONES OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPUR AND MURSHIDABAD - JIAGANJ BLOCK OF MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION-I, PHE Dte. IN CONNECTION WITH JJM. | Assistant Engineer-I | JE | ORD/000283/2023-2024 | 983/BD-I | 30/10/2023 | 01/07/2025 | WPIL LIMITED | 12076.79 | 0 | 0 | 16
15 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Formal work order for Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Raw Water Intake, WTP, Raw Water Rising Main, Clear Water Rising Main (CWR at WTP to different OHR sites), OHR, Chlorine cum Switch Room, Boundary Wall etc. including all allied related and enabling works for surface water based piped water supply scheme for entire NABAGRAM Block, Part of Berhampore & Murshidabad-Jiaganj Blocks of District Murshidabad followed by 6(Six) months of Trial Run and subsequent Operation & Maintenance of 5(Five) years. | Assistant Engineer-I | JE | ORD/000288/2022-2023 | 1802/BD-I | 31/03/2023 | 31/03/2025 | GBC INFRASTRUCTURE PVIVATE LIMITED | 15290.9 | 0 | 0 | 20
16 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 61/BD-1/36 | 27/04/2023 | 27/04/2023 | Resource Division | 8607.44 | 0 | 0 | 0
17 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 360/BD-1 | 05/03/2024 | 05/03/2024 | Resource Division | 123.2 | 0 | 0 | 0
18 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Bulk power connection charge for Nabagram Intake 276KVA Application No-R000012129 Con Id-950086101 |  |  | BILL/01060/2023-2024 | 198/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 28.06 | 0 | 0 | 0
19 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Bulk power connection charge for Nabagram WTP 1047KVA Application No- R000012128 Con Od-950085502 |  |  | BILL/01067/2023-2024 | 199/WBSEDCL-JJM | 19/12/2023 | 19/12/2023 | WBSEDCL | 86.39 | 0 | 0 | 0
20 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT MEHENDIPUR OHR SITE |  |  | BILL/01775/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 3.86 | 0 | 0 | 0
21 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT RAJDHARPUR OHR SITE |  |  | BILL/01776/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 9.09 | 0 | 0 | 0
22 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT GRAMDIGHI OHR SITE |  |  | BILL/01777/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 5.64 | 0 | 0 | 0
23 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT CHANAK OHR SITE |  |  | BILL/01778/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 8.09 | 0 | 0 | 0
24 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT AMIRABAD OHR SITE |  |  | BILL/01779/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 3.09 | 0 | 0 | 0
25 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT BICHHUTI OHR SITE |  |  | BILL/01780/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 3.12 | 0 | 0 | 0
26 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT BURARDANGA OHR SITE |  |  | BILL/01781/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 4.54 | 0 | 0 | 0
27 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT JARULIA OHR SITE |  |  | BILL/01782/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 4.29 | 0 | 0 | 0
28 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT KHOSBAG OHR SITE |  |  | BILL/01783/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 5.96 | 0 | 0 | 0
29 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | NEW CONNECTION AT GARSHYAMA OHR SITE |  |  | BILL/01784/2024-2025 |  | 26/03/2025 | 26/03/2025 | WBSEDCL | 3.67 | 0 | 0 | 0
30 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Raw Water Pumping Station under Nabagram Surface Water Based W/S Scheme, Dist. Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000979/2023-2024 | 3861/MEDB | 07/11/2023 | 07/05/2024 | ALOK ENTERPRISE | 258.96 | 0 | 0 | 10
31 | MURSHIDABAD | Berhampore,Murshidabad Jiaganj,Nabagram | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD | SM/12360 | New | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Water Treatment Plant under Nabagram Surface Water Based W/S Scheme under MEDB, P.H.E. Dte., Dist. Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000980/2023-2024 | 3862/MEDB | 07/11/2023 | 02/05/2025 | ORIENTAL ENGINEERING CO. | 391.5 | 0 | 0 | 5
Total | [13 empty] | 37018.43 | 0 | 0