## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Improvement of R.C.C Elevated Reservoir (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Kasba Bahadurpur water supply scheme of Bhagwangola-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I |  | ORD/000006/2024-2025 | 894/BD-I | 06/06/2024 | 06/07/2024 | DEBOJYOTI CONSTRUCTION | 8.26 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Kasba Bahadurpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE | ORD/000108/2022-2023 | 1361/BD-I | 21/12/2022 | 20/01/2023 | KAKALI ENTERPRISE | 2.41 | 1.66 | 68.86 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Allied work for the work of Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate Bored Cast-in-situ_M30_grade 450 mm.R.C.C pile for construction of OHR, Pump House, Boundary Wall, Service Road and laying of distribution pipeline under Jal Jeevan Mission within Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I |  | ORD/000122/2024-2025 | 1470/BD-I | 06/09/2024 | 05/11/2024 | DECON INDIA | 96.16 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Formal Work order for Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000162/2022-2023 | 1454/BD-I | 17/01/2023 | 17/01/2024 | DECON INDIA | 444.11 | 152.14 | 34.26 | 30
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasba Bahadurpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | Junior Engineer-I | ORD/000285/2022-2023 | 1809/BD-I | 31/03/2023 | 30/04/2023 | HARUN ALL RASHID & BROTHERS | 17.66 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBA BAHADURPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000875/2021-2022 | 259/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.96 | 2.95 | 99.6 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 196/BD-I/11 | 09/02/2024 |  | Resource Division | 70.91 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | NEW CONNECTION AT KASBA BAHADURPUR PH-1 |  |  | BILL/00664/2024-2025 | null | 03/09/2024 |  | WBSEDCL | 5.46 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | NEW CONNECTION AT KASBA BAHADURPUR PH-I |  |  | BILL/00670/2024-2025 | null | 03/09/2024 |  | WBSEDCL | 5.46 | 0 | 0 | null
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur | SM/12582 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Kasba Bahadurpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000039/2023-2024 | 3732/MEDB | 03/11/2023 | 01/02/2024 | S.P. ENTERPRISE (BAGUIHATI) | 22.37 | 0 | 0 | 0
Total | [13 empty] | 675.77 | 156.75 | 23.2