## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Augmentation of Dakshin Sahar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer-I |  | ORD/000026/2023-2024 | 103/BD-I | 04/05/2023 | 09/03/2024 | RAJ KUMAR MONDAL | 352.91 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dakshin Sahar Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000042/2023-2024 | 67/BD-I | 27/04/2023 | 27/05/2023 | SUJIT KUMAR SAHA | 9 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Augmentation of Dakshin Sahar Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000105/2023-2024 | 105/BD-I | 08/05/2023 | 04/11/2023 | A ONE CONSTRUCTION | 303.14 | 0 | 0 | 42
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Sahar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000115/2022-2023 | 1412/BD-I | 04/01/2023 | 14/01/2023 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 3.61 | 1.23 | 34.11 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN SAHAR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I |  | ORD/000173/2022-2023 | 1077/BD-I | 29/09/2022 | 09/10/2022 | NATSOL CONSULTANT | 2.71 | 2.71 | 100 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) forDakshinSahar water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I |  | ORD/000257/2023-2024 | 1027/BD-I | 01/11/2023 | 01/12/2023 | DEBJIT DAS | 7.5 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | DAKSHINSAHAR PART-A PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BHAGAWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I |  | ORD/000458/2023-2024 | 462/BD-I | 15/03/2024 | 14/05/2024 | RELIABLE ENTERPRISE | 21.99 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 196/BD-I/2 | 09/02/2024 |  | Resource Division | 41.96 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. | SM/12585 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN SAHAR ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000026/2023-2024 | 3728/MEDB | 03/11/2023 | 01/02/2024 | JOY BISHNU ENGINEERING CO. | 12.42 | 0 | 0 | 0
Total | [13 empty] | 755.24 | 3.94 | 0.52