## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Replacement of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 07.00 Cum/hr) at Ramnapara Water Supply Scheme under Jal Jeevan Mission of Bhagwangola-II Block under Berhampore Div-I, Murshidabad PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000025/2024-2025 | 972/BD-I | 18/06/2024 | 18/07/2024 | ULTRA CONSTRUCTION | 14.12 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Ramnapara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE | ORD/000113/2022-2023 | 1410/BD-I | 04/01/2023 | 03/02/2023 | KAKALI ENTERPRISE | 2.23 | 1.23 | 54.95 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Augmentation of RAMNAPARA Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000190/2022-2023 | 1456/BD-I | 17/01/2023 | 16/07/2023 | S.K ENTERPRISE (RANITALA) | 34.01 | 16.89 | 49.66 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Repair And Renovation Works Of RCC Elevated Reservoir (30 Cum) for Ramnapara water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000267/2023-2024 | 989/BD-I | 30/10/2023 | 29/11/2023 | DAYAMAYEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED | 3.06 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAPARA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000887/2021-2022 | 270/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.41 | 98.54 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. | SM/12740 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 196/BD-I/3 | 09/02/2024 |  | Resource Division | 1.74 | 0 | 0 | 0
Total | [13 empty] | 57.62 | 20.53 | 35.64