## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | Augmentation of Kazipara zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in JALANGI Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer | JE | ORD/000022/2023-2024 | 96/BD-I | 04/05/2023 | 03/05/2024 | MS JAKIR HOSSAIN | 291.08 | 149.62 | 51.4 | 70
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of KAZIPARA ZONE-II PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000059/2024-2025 | 1136/BD-I | 15/07/2024 | 13/09/2024 | U.S BUILDERS | 7.92 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000295/2022-2023 | 1777/BD-I | 27/03/2023 | 06/04/2023 | M/S SOBHA & CO | 2.74 | 1.35 | 49.45 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | KAZIPARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of JALANGI Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer |  | ORD/000459/2023-2024 | 463/BD-I | 15/03/2024 | 14/05/2024 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 23.55 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 194/BD-I/8 | 09/02/2024 |  | Resource Division | 31.41 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | NEW SERVICE CONNECTION AT KAJIPARA PH1 Z2 ID304244954 |  |  | BILL/01505/2023-2024 | 404/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 5.18 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. | SM/14047 | Augmentation | NEW SERVICE CONNECTION AT KAJIPARA PH2 Z2 ID 304244955 |  |  | BILL/01507/2023-2024 | 405/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 6.56 | 0 | 0 | 0
Total | [13 empty] | 1088.66 | 150.97 | 13.87