## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Augmentation of Sarkarpara Piped water supply scheme to accommodate construction of boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000224/2022-2023 | 1557/BD-I | 20/02/2023 | 19/08/2023 | AZAD ENTERPRISE | 63.96 | 19.04 | 29.76 | 75
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Repair And Renovation Works Of OHR (45 Cum) of Ground Water Based Supply Scheme for Sarkarpara of Jalangi block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. |  |  | ORD/000249/2023-2024 | 1092/BD-I | 24/11/2023 | 24/12/2023 | PARUL ELECTRICAL INSTALLER | 5.41 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SARKARPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000282/2022-2023 | 1370/BD-I | 21/12/2022 | 31/12/2022 | M/S SOBHA & CO | 2.46 | 2.39 | 97.11 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 194/BD-I/9 | 09/02/2024 |  | Resource Division | 14.79 | 0 | 0 | 0
Total | [13 empty] | 806.85 | 21.43 | 2.66