## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Improvement of OHR (136.2 Cum) of Ground Water Based Supply Scheme for Augmentation of Dakshin Gopalpur of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000002/2024-2025 | 890/BD-I | 06/06/2024 | 06/07/2024 | RAJEN DAS | 7.27 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Dakshin Gopalpur PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000050/2024-2025 | 1113/BD-I | 10/07/2024 | 24/08/2024 | KHANDAKAR CONSTRUCTION | 22.05 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Augmentation of DAKSHIN GOPALPUR Piped water supply scheme for laying of design pipeline, rising main and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000241/2022-2023 | 1598/BD-I | 28/02/2023 | 27/08/2023 | GOUTAM CHAKRABORTY | 134.6 | 88.66 | 65.87 | 32
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN GOPALPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000275/2022-2023 | 1504/BD-I | 07/02/2023 | 17/02/2023 | M/S SOBHA & CO | 2.67 | 2.57 | 96.56 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Renovation for Modified Sujapur Sadipur Model after washing of AIRP (Capacity 29.06 Cum/hr.) at Dakshin Gopalpur Water Supply Scheme under Jal Jivan Mission of Raninagar-I Block under Raghunathganj Sub-Division under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000439/2023-2024 | 410/BD-I | 13/03/2024 | 12/05/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 51.69 | 15.9 | 30.75 | 75
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . | SM/14066 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 194/BD-I/4 | 09/02/2024 |  | Resource Division | 36.44 | 0 | 0 | 0
Total | [13 empty] | 974.96 | 107.13 | 10.99