## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Nasipur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000117/2022-2023 | 1368/BD-I | 21/12/2022 | 20/01/2023 | CHATTERJEE ENTERPRISE | 2.46 | 1.21 | 49.2 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000204/2022-2023 | 1374/BD-I | 21/12/2022 | 31/12/2022 | ENVIROTECH SOLUTIONS | 2.94 | 2.62 | 89.24 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Augmentation of Nasipur Zone_I Piped water supply scheme to accommodate construction of Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000245/2022-2023 | 1625/BD-I | 02/03/2023 | 29/08/2023 | DHIMAN SARKAR | 176.03 | 71.29 | 40.5 | 26
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) Ground water supply scheme for Nashipur Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000266/2023-2024 | 988/BD-I | 30/10/2023 | 29/11/2023 | SELIM SARKAR | 9.8 | 0 | 0 | 90
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 1510/BD-I/6 | 12/09/2024 |  | Resource Division | 4.99 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. | SM/14070 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 201/BD-1/13 | 10/02/2024 |  | Resource Division | 60.04 | 0 | 0 | 0
Total | [13 empty] | 256.26 | 75.12 | 29.32