## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of Arsenic cum Iron Removal Plant(AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000025/2023-2024 | 313/BD-I | 14/06/2023 | 12/10/2023 | MODERN CONSTRUCTION | 261.29 | 24.24 | 9.28 | 27
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000277/2022-2023 | 1760/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.46 | 2.46 | 100 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bansgara Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | Assistant Engineer | Junior Engineer-II | ORD/000313/2023-2024 | 1149/BD-I | 04/12/2023 | 03/01/2024 | NADIA TUBEWELLS | 11.56 | 5.07 | 43.84 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 194/BD-I/7 | 09/02/2024 |  | Resource Division | 32.78 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | load enhancement bansgara z2 ph 1 |  |  | BILL/01597/2023-2024 | null | 05/03/2024 |  | WBSEDCL | 1.8 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | LOAD ENHANCEMENT AT BANSGARA Z2 PH1 ID 312397840 |  |  | BILL/01637/2023-2024 | 481/WBSEDCL-JJM | 21/03/2024 |  | WBSEDCL | 1.8 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. | SM/14734 | Augmentation | LOAD ENHANCEMENT BANSGARA AIRP ID 3004571720 |  |  | BILL/01638/2023-2024 | 482/WBSEDCL-JJM | 21/03/2024 |  | WBSEDCL | 1.11 | 0 | 0 | 0
Total | [13 empty] | 312.8 | 31.77 | 10.16