## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | Augmentation | Improvement of OHR (450 Cum) of Ground Water Based Supply Scheme for Augmentation of Kazipara Zone-I of Jalangi block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer | JE | ORD/000021/2024-2025 | 934/BD-I | 10/06/2024 | 10/07/2024 | M/S. MONDAL ENTERPRISE | 11.42 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of KAZIPARA ZONE-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | JE_Pravin Kumar Gupta | ORD/000041/2024-2025 | 1059/BD-I | 03/07/2024 | 17/08/2024 | MUNNA AGROTECH ENTERPRISE | 16.5 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | Augmentation | Augmentation of Kazipara Zone_I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000121/2023-2024 | 505/BD-I | 24/07/2023 | 20/01/2024 | M/S S.DAS & ENTERPRISE | 178 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000280/2022-2023 | 1764/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.74 | 1.37 | 50 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. | SM/14950 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 61/BD-1/12 | 27/04/2023 |  | Resource Division | 35.26 | 0 | 0 | 0
Total | [13 empty] | 243.92 | 1.37 | 0.56