## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 34 Cum/hr.) with allied work at Ramnachandrapur Zone-III Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000013/2024-2025 | 913/BD-I | 07/06/2024 | 07/07/2024 | SAMAR MUKHERJEE | 13.04 | 0 | 0 | 90
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Improvement of OHR (180 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-III PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-II |  | ORD/000027/2024-2025 | 983/BD-I | 19/06/2024 | 18/08/2024 | U.S BUILDERS | 9.46 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Augmentation of Ramnachandpur Zone-III Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE,Junior Engineer-II | ORD/000207/2022-2023 | 1622/BD-I | 02/03/2023 | 29/08/2023 | SAMAR MUKHERJEE | 112.68 | 97.69 | 86.7 | 87
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-III Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000236/2022-2023 | 1594/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.53 | 2.53 | 100 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) for Ramnachandpur Zone-III water supply scheme of Nawda block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-II | JE | ORD/000256/2023-2024 | 1016/BD-I | 31/10/2023 | 30/11/2023 | NATIONAL ENTERPRISES | 7.4 | 0 | 0 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-III Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-II | JE | ORD/000388/2023-2024 | 150/BD-I | 05/02/2024 | 06/03/2024 | NADIA TUBEWELLS | 9 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 196/BD-I/17 | 09/02/2024 |  | Resource Division | 14.91 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . | SM/15229 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II , ZONE-III under RAMNACHANDPUR_ ground water based water supply scheme under Block_ NOWDA Dist. - Murshidabad under MEDB, PHE Dte. |  |  | ORD/000674/2023-2024 | 4344/MEDB | 29/12/2023 | 28/03/2024 | SUNIL RABIDAS | 19.44 | 0 | 0 | 0
Total | [13 empty] | 188.47 | 100.22 | 53.18