## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | BELIA SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000092/2023-2024 | 214/BD-I | 17/05/2023 | 15/08/2023 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 40.8 | 0 | 0 | 30
2 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | BELIA SYAMPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I |  | ORD/000132/2023-2024 | 611/BD-I | 02/08/2023 | 29/01/2024 | ROY CONSTRUCTION (AVIJIT ROY) | 69 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS | SM/15996 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 61/BD-1/17 | 27/04/2023 |  | Resource Division | 11.74 | 0 | 0 | 0
Total | [13 empty] | 121.54 | 0 | 0