## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola - I | Central Drilling | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | New | KULGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000089/2023-2024 | 212/BD-I | 17/05/2023 | 15/08/2023 | NATIONAL CONSTRUCTION | 36.84 | 6.96 | 18.89 | 60
3 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | New | KULGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000098/2023-2024 | 111/BD-I | 10/05/2023 | 14/02/2024 | RAJ KUMAR MONDAL | 251.46 | 30.74 | 12.22 | 20
4 | MURSHIDABAD | Bhagawangola - I | Berhampore Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 61/BD-1/29 | 27/04/2023 |  | Resource Division | 12.73 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola - I | Berhampore Mechanical | KULGACHI AND ITS ADJOINING MOUJAS PWSS | SM/16302 | New | KULGACHI PWSS |  |  | BILL/01454/2023-2024 | 346/WBSEDCL-JJM | 15/02/2024 |  | WBSEDCL | 3.25 | 0 | 0 | 0
Total | [13 empty] | 1024.51 | 37.7 | 3.68