## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000076/2023-2024 | 182/BD-I | 17/05/2023 | 15/08/2023 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 28.45 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000077/2023-2024 | 183/BD-I | 17/05/2023 | 15/08/2023 | PRADIP DAS | 28.45 | 0 | 0 | 0
3 | MURSHIDABAD | Berhampore | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-C) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000078/2023-2024 | 184/BD-I | 17/05/2023 | 15/08/2023 | GOUTAM KUMAR CHAUDHURI | 28.32 | 0 | 0 | 0
4 | MURSHIDABAD | Berhampore | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000175/2023-2024 | 3036/MEDB | 02/08/2023 | 31/10/2023 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
5 | MURSHIDABAD | Berhampore | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. | SM/16429 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000189/2023-2024 | 588/MEDB | 31/01/2024 | 30/04/2024 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
Total | [13 empty] | 97.83 | 0 | 0