## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Central Drilling | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | SAMASKAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000102/2023-2024 | 220/BD-I | 17/05/2023 | 15/08/2023 | BINAPANI ENTERPRISE | 52.7 | 0 | 0 | 5
3 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | SAMASKAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART -A) | Assistant Engineer-II | JE | ORD/000159/2023-2024 | 669/BD-I | 09/08/2023 | 08/08/2024 | BAHETI CONSTRUCTION | 209.2 | 0 | 0 | 20
4 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | SAMASKAR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-II | JE | ORD/000294/2022-2023 | 1824/BD-I | 31/03/2023 | 27/09/2023 | ARINDAM MAJUMDAR | 109.77 | 0 | 0 | 0
5 | MURSHIDABAD | Berhampore | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 61/BD-1/6 | 27/04/2023 |  | Resource Division | 15.38 | 0 | 0 | 0
6 | MURSHIDABAD | Berhampore | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | NEW CONNECTION SAMASKAR PH-I |  |  | BILL/01657/2023-2024 | 10/WBSEDCL-JJM | 09/04/2024 |  | WBSEDCL | 7.19 | 0 | 0 | 0
7 | MURSHIDABAD | Berhampore | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS | SM/16454 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SAMSASKAR ground water based water supply scheme under Block_ Berhampore Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000701/2023-2024 | 4339/MEDB | 29/12/2023 | 28/03/2024 | DEBJYOTI BASU | 20.87 | 0 | 0 | 10
Total | [13 empty] | 21754.88 | 0 | 0