## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Berhampore | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16497 | New | Mini Piped Water Supply Scheme for Char Sujapur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000072/2023-2024 | 167/BD-I | 16/05/2023 | 14/08/2023 | ALOK BANERJEE ENTERPRISE | 30.49 | 0 | 0 | 0
2 | MURSHIDABAD | Berhampore | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. | SM/16497 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at CharSujapur Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000180/2023-2024 | 3041/MEDB | 02/08/2023 | 31/10/2023 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
Total | [13 empty] | 36.81 | 0 | 0