## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Central Drilling | DIAR FATEPUR PWSS | SM/16781 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 21/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 0 | 0
2 | MURSHIDABAD | Lalgola | Central Drilling | DIAR FATEPUR PWSS | SM/16781 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 1.26 | 0.18 | 10
3 | MURSHIDABAD | Lalgola | Berhampore Division I | DIAR FATEPUR PWSS | SM/16781 | New | DIAR FATHEPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000085/2023-2024 | 205/BD-I | 17/05/2023 | 15/08/2023 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 40.93 | 9.07 | 22.15 | 35
4 | MURSHIDABAD | Lalgola | Berhampore Division I | DIAR FATEPUR PWSS | SM/16781 | New | DIAR FATHEPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer | JE | ORD/000129/2023-2024 | 606/BD-I | 02/08/2023 | 28/05/2024 | M/S J.S ENTERPRISE | 362.92 | 54.66 | 15.06 | 30
5 | MURSHIDABAD | Lalgola | Berhampore Division I | DIAR FATEPUR PWSS | SM/16781 | New | DIAR FATHEPUR PWSS to accommodate FHTC Laying distribution system under Jal Jeevan Mission of Lalgola Block Murshidabad District under Berhampore Division-I, PHE Dte. (Part-B) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000258/2023-2024 | 973/BD-I | 18/10/2023 | 24/07/2024 | SWAPAN DAS | 95.38 | 0 | 0 | 30
6 | MURSHIDABAD | Lalgola | Berhampore Division I | DIAR FATEPUR PWSS | SM/16781 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 61/BD-1/32 | 27/04/2023 |  | Resource Division | 38.25 | 0 | 0 | 0
7 | MURSHIDABAD | Lalgola | Berhampore Division I | DIAR FATEPUR PWSS | SM/16781 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 304/BD-1/4 | 22/02/2024 |  | Resource Division | 19.21 | 0 | 0 | 0
8 | MURSHIDABAD | Lalgola | Berhampore Mechanical | DIAR FATEPUR PWSS | SM/16781 | New | Quotation for WBSEDCL for Diar Fatepur Application No- 3004544437 |  |  | BILL/01171/2023-2024 | 233/WBSEDCL-JJM | 15/01/2024 |  | WBSEDCL | 4.89 | 0 | 0 | 0
Total | [13 empty] | 1740.5 | 64.98 | 3.73